Annex B

Committed Projects under the High Priority Programme to be transferred to CWRF (Note 1)

Item Description and Project Title

Project Scope

Commence-ment

| date | Target Completion date | Progress as at 31.10.97 |  | (a) Stage I of SSDS |  |  |  |  |  | 001SS - Strategic Sewage Disposal Scheme Stage I: Principal Collection and Treatment System - Advance Works |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Site facilities for Resident Site Staff; excavation of production shafts and pumping station foundation; diaphragm walls; piled foundation for sedimentation tanks

|  | 03/94 |
| --- | --- |

10/1997

(Actual)

Works

Substantially

| completed |  | 002SS - Strategic Sewage Disposal Scheme Stage I: Chemical Dosing Facilities |
| --- | --- | --- |

Provision of chemical dosing facilities at Stonecutters Island Sewage Treatment Works

|  | 11/95 | 01/1998 | 81% works completed |  |
| --- | --- | --- | --- | --- |

010SS - Strategic Sewage Disposal Scheme Stage I: Sewer Tunnel System from Chai Wan and Tseung Kwan O to Kwun Tong

Sewage tunnel from Chai Wan and Tseung Kwan O to Kwun Tong

| (Note 2) | 01/95 |
| --- | --- |

07/2000

|  | (Note 3) |  | 011SS - Strategic Sewage Disposal Scheme Stage I: Stonecutters Island Sewage Treatment Works Sludge Treatment Facilities |
| --- | --- | --- | --- |

Provision of sludge treatment facilities at Stonecutters Island Sewage Treatment Works

|  | 06/95 |
| --- | --- |

10/1997

(Actual)

Works

Substantially

| completed |  |
| --- | --- |

012SS Strategic Sewage Disposal Scheme Stage I: Stonecutters Island Sewage Treatment Works - Sedimentation Tanks (Civil works)

|  | Construction of foundation works, structural and site works of the sedimentation tanks at Stonecutters Island Sewage Treatment Works | 02/95 |
| --- | --- | --- |

06/1997

(Actual)

Works

Substantially

| completed |  |
| --- | --- |

013SS - Strategic Sewage Disposal Scheme Stage I: Pumping Stations E&M Equipment

Provision of E&M equipment for pumping stations at the Stonecutters Island STW, Kwun Tong and Tseung Kwan O and a central monitoring and control system

|  | 01/95 | 05/1998 | 63% works completed |  |
| --- | --- | --- | --- | --- |

014SS - Strategic Sewage Disposal Scheme Stage I: Stonecutters Island Sewage Treatment Works - Pumping Stations, Buildings and Site Development

|  | Construction of pumping stations and buildings at Stonecutters Island and site development facilities | 04/95 | 03/1998 | 96% works completed |  | 015SS - Strategic Sewage Disposal Scheme Stage I: Upgrading Existing Preliminary Treatment Works |
| --- | --- | --- | --- | --- | --- | --- |

Upgrading of existing preliminary treatment works at Chai Wan, Shau Kei Wan, Tseung Kwan O, Kwun Tong, Tsing Yi, Kwai Chung and To Kwa Wan

|  | 03/95 | 04/1998 | 79% works completed |  | 016SS - Strategic Sewage Disposal Scheme Stage I: Sedimentation Tanks E&M Equipment |
| --- | --- | --- | --- | --- | --- |

Provision of E&M equipment for the sedimentation tanks at the Stonecutters Island Sewage Treatment Works

|  | 02/95 | 04/1998 | 79% works completed |  |
| --- | --- | --- | --- | --- |

017SS - Strategic Sewage Disposal Scheme Stage I: Sewer Tunnel System from Kwun Tong and Kwai Chung to Stonecutters Island

Sewage tunnel from Kwun Tong and Kwai Chung to Stonecutters Island

(Note 2)

|  | 01/95 |
| --- | --- |

07/2000

|  | (Note 4) |  |  |  |  |  |  |  | 018SS - Strategic Sewage Disposal Scheme Stage I: Construction Supervision of the Main Works |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Construction supervision of 11 main works contracts of the SSDS Stage 1 and includes the Consultant’s fee for construction supervision and Resident Site Staff costs.

|  | 01/95 | 02/2000 |
| --- | --- | --- |

70% works completed

|  |  | 021SS - Strategic Sewage Disposal Scheme Stage I: Outfall |
| --- | --- | --- |

Construction of a 1740 m long outfall tunnel together with two 3.25 in diameter riser shafts and a 1200 m long diffuser pipeline

|  | 04/95 | 05/1998 | 96% works completed |  | 022SS - Strategic Sewage Disposal Scheme Stage I: Construction of Sludge Transfer Facilities and Supply of Sludge Containers |
| --- | --- | --- | --- | --- | --- |

Provision of sludge handling and transfer facilities at Stonecutters Island Sewage Treatment Works and South East New Territories and West New Territories landfills and supply of 400 numbers of sludge containers

|  | 10/95 | 05/1999 | 65% works completed |  |
| --- | --- | --- | --- | --- |

023SS - Strategic Sewage Disposal Scheme Stage I: Pilot Plant Study on Chemical Dosing and Disinfection

(Category D)

Pilot plant study on chemical dosing and disinfecti